## Sheet1
Risk | Risk Description | Probability | Impact | Rating | Mitigation Plan | Plan
Team member is sick | Impact on schedule. | very likely | Moderate | High | Mitigate | 1- Ensure that other team memebers are good. 2- If available, another team member may do his work until he gets better.
Competitor | Impact on the app at market. | Moderate | Moderate | Medium | Mitigate | Ensure the quality of the product and that all features are working.
Can't find a supplier for a particular piece of the product. | 1-Impact on schedule. 2-Impact on the app. | Moderate | Extreme | High | Avoid | Ensure that there is at least two suppliers for each piece of the product in the design phase.