## Sheet1
Activity | # of units | Unit Price ($) | Estimated Cost
1. Plan | 30 |  | 300
1.1 Create Stakeholder engagement plan. | 5 | 10 | 50
1.2 Communicate with customer to get the full requirements. | 5 | 10 | 50
1.3 Decide the team members who will work on this project. | 20 | 10 | 200
2. Design | 100 |  | 3000
2.1 Design the software architecture. | 50 | 40 | 2000
2.2 Design the Sequence diagram for the application. | 25 | 20 | 500
2.3 Divide the work into modules. | 25 | 20 | 500
3. Implement | 2000 |  | 30000
3.1 Develop the application to be used by users. | 1000 | 15 | 15000
3.2 Develop an application to be used by shops (if it’s required). | 1000 | 15 | 15000
4. Test | 900 |  | 18000
4.1 Start testing each module in the app. | 500 | 25 | 12500
4.2 Test the application to be used by shops. | 400 | 13.75 | 5500
5. Deploy | 1000 |  | 20000
5.1 Get approval from the customer that the requirements are met. | 300 | 20 | 6000
5.2 Start deploying the app for a small number of shops. | 300 | 20 | 6000
5.3 Get feedback to deploy the app on a larger scale. | 400 | 20 | 8000
Overall Cost |  |  | 71300
Assumptions list
1. HR hired qualified team.
2. Get the required tools from suppliers with a reasonable and fixed price.