## list
ID | Activity List | Duration | Precedent ID | Relationship | Lead / Lag
id | activity | duration | precedentAct | relationship | L
1 | Create stakeholder engagement plan. | 2 | 0
2 | Communicate with customer to get fill requirements | 2 | 1 | FS | 0
3 | Decide which team members who will work on this project. | 6 | 2 | FS | 0
4 | Design Software architecture | 7 | 3 | FS | 0
5 | Design the sequence diagram for the application | 5 | 2,3 | FS,FS | 0,0
6 | Dvidie the work into modules | 4 | 4,5 | FS,FS | 0,0
7 | Develop the application to be used by users. | 20 | 6 | FS | 0
8 | Develop an application to be used by shops. | 10 | 6 | FS | 0
9 | Start testing ech module in the app. | 5 | 7 | FS | 0
10 | Test the application to be used by shops. | 5 | 8 | FS | 0
11 | Get approval from customer that requirements are met. | 2 | 9,10 | FS,FS | 0,0
12 | Start deploying the app for a small number of shops. | 2 | 11 | FS | 0
13 | Get feedback to deploy the app on a larger scale. | 2 | 12 | FS | 0
Note on D1: Enter the ID of precedent activitiy. If there are more than one, enter them in comma separated style. e.g. 1,2. When you enter the first activity, enter 0 and the Relationship and the Lead / Lag column should remain blank.
Note on E1: Enter FS (*Finish to Start), SS (*Start to Start), SF (*Start to Finish) or FF (*Finish to Finish). If there are more than one, enter them in comma separated style. e.g. FS,SS.
Note on F1: When you enter lead time, use negative number. When you enter lag time, use positive number. If there are more than one, enter them in comma separated style. e.g. 1,-2.

## diagram
Project Schedule (PDM) |  |  |  |  | (Red is critical)
| ID | 1 | Duration | 2
| ES | 0 | EF | 2
Create stakeholder engagement plan.
| LS | 0 | LF | 2
(ID_1) FS, 0
| ID | 2 | Duration | 2
| ES | 2 | EF | 4
Communicate with customer to get fill requirements
| LS | 2 | LF | 4
(ID_2) FS, 0
| ID | 3 | Duration | 6
| ES | 4 | EF | 10
Decide which team members who will work on this project.
| LS | 4 | LF | 10
|  |  | (ID_3) FS, 0 |  |  |  |  | (ID_2) FS, 0 / (ID_3) FS, 0
| ID | 4 | Duration | 7 |  | ID | 5 | Duration | 5
| ES | 10 | EF | 17 |  | ES | 10 | EF | 15
| Design Software architecture |  |  |  |  | Design the sequence diagram for the application
| LS | 10 | LF | 17 |  | LS | 12 | LF | 17
(ID_4) FS, 0 / (ID_5) FS, 0
[6 empty] | ID | 6 | Duration | 4
[6 empty] | ES | 17 | EF | 21
Dvidie the work into modules
[6 empty] | LS | 17 | LF | 21
[8 empty] | (ID_6) FS, 0 |  |  |  | (ID_6) FS, 0
[6 empty] | ID | 7 | Duration | 20 | ID | 8 | Duration | 10
[6 empty] | ES | 21 | EF | 41 | ES | 21 | EF | 31
[6 empty] | Develop the application to be used by users. |  |  |  | Develop an application to be used by shops.
[6 empty] | LS | 21 | LF | 41 | LS | 31 | LF | 41
[8 empty] | (ID_7) FS, 0 |  |  |  | (ID_8) FS, 0
[6 empty] | ID | 9 | Duration | 5 | ID | 10 | Duration | 5
[6 empty] | ES | 41 | EF | 46 | ES | 31 | EF | 36
[6 empty] | Start testing ech module in the app. |  |  |  | Test the application to be used by shops.
[6 empty] | LS | 41 | LF | 46 | LS | 41 | LF | 46
(ID_9) FS, 0 / (ID_10) FS, 0
[10 empty] | ID | 11 | Duration | 2
[10 empty] | ES | 46 | EF | 48
Get approval from customer that requirements are met.
[10 empty] | LS | 46 | LF | 48
(ID_11) FS, 0
[10 empty] | ID | 12 | Duration | 2
[10 empty] | ES | 48 | EF | 50
Start deploying the app for a small number of shops.
[10 empty] | LS | 48 | LF | 50
(ID_12) FS, 0
[10 empty] | ID | 13 | Duration | 2
[10 empty] | ES | 50 | EF | 52
Get feedback to deploy the app on a larger scale.
[10 empty] | LS | 50 | LF | 52